## Sheet1
Sr No | Date | Screen | Tasks | Roles | Owner | Dev Target Date | Test Release
5 | 2020-12-24 | All | Enable tokenization for Cardnumber, Expiredate, Account number, PAN and Aadhaar, Email address using Insert token API | Backend | Arshaq | 14th Dec 2020 | 15th Dec 2020
|  |  | 1. Saving Tokenized Values in a new table. - 24th dec |  |  | 29th Dec 2020 | 29th Dec 2020
2. Create a wrapper to call detokenization service from front end
2.1 On successful tokenization response, proceed with step 3 (static masking)
2.2 In case of err from tokenization api (retry)
front end to handle -
App tracker should not be masked
2.3 On BAcked Static MAsking to be triggred only after SR in submitted stated
2.4 When customer has not authorized - SR in created state ... tokenization not to be triggred and backend static masking should not be enabled.
3. Masking the values in the original SR table.
6 | 2020-12-24 | All | Tokenization - Integration of Aadhaar value get vaule and insert value | Backend | Arshaq | 14th Dec 2020 | 15th Dec 2020
29th Dec 2020
28th Dec 2020
9 | 2020-12-11 | All | In API Logger - response has to be masked for for create virtual Debit card | Backend | Vishal N / Sanjay M | 28th Dec 2020 | 29th Dec 2020
17th Dec 2020
10 | 2020-12-11 | All | In API Logger - Aadhaar number has to be masked in request xxxx xxxx 1234 | Backend | Vishal N / Sanjay M | 28th Dec 2020 | 29th Dec 2020
17th Dec 2020
10 | 2020-12-11 | Backend | UPIintegration feature - 2.5 Once funding is provided customer should not be able to delete the records | Backend | Arshaq | 29th Dec 2020 | 29th Dec 2020
13 | 2020-12-24 | Final Screen | Virtual Debit card debit card creation based on product selection - Masked number should be displayed as sent by vinod sir | Backend | Ganesh | 29th Dec 2020 | 29th Dec 2020
19 | 2020-12-24 | Final Screen | VideoKYC with Full KYC AC- Transaction patterns -> Initial Funding-> Preview Page -> account creation -> VideoKYC button on success page | FE | Priyanka | 29th Dec 2020 | 29th Dec 2020
| 2020-12-16 | Aadhaar Personal Details | Pincode, City, State and Country populated from Aadhaar API should be retained even if any of these values is not found in the master. | Back | Ganesh/ Deepen | 2020-12-29 | 2020-12-29
End
| 2020-12-16 | Aadhaar Personal Details >> Current Address | City, State and Country should get autopopulated on entering pin code during Current Address updation. Evaluate usage of microservices for this feature - based upon the data that is given for mapping | Back | Jasmine/Ganesh | 2020-12-29 | 2020-12-29
End
| 2020-12-16 | Aadhaar Personal Details >> Current Address | City, State and Country should get autopopulated on entering pin code during Current Address updation. Evaluate usage of microservices for this feature - based upon the data that is given for mapping | Front End | Parth/Deepen | 2020-12-29 | 2020-12-29
43 | 2020-12-16 | Personal & Address Details | FatherName / Spouse Name should be a choice | Front End | Priyanka | 2020-12-28 | 2020-12-29
| 2020-12-16 | Personal & Address Details | Current Address Selection - Should be default Yes, on choing No, address details should be populated. | Front End | Priyanka | 2020-12-28 | 2020-12-29
In case Current Address is same as Permanent Address, do not show the details on screen
| 2020-12-16 | Preview Form | Once we receive Reference Key from EKYC API, the reference number should be used in all other screens | Back End | arshaq | 2020-12-28 | 2020-12-29
| 2020-12-16 | Personal details and address details page | Country Field to be defaulted in All address fields as INDIA | Back End | Vishal | 2020-12-28 | 2020-12-29
Autopopulate and make it non editable
| 2020-12-24 |  | Name Mismatch To be configurable - 65% and more to be allowed and the option of % should be configurable. - | Front End | Priyanka | 28th Dec 2020 | 29th Dec 2020
If name mismatch is below 65% i.e. 64 and less then stop journey
with pop-message as per current frontend message "'To avail this service please visit your nearest YES BANK branch along with proof of identify documents(that includes any one of following documents - Aadhaar Card, Driving License, Voter Identify Card, Passport or NREGA card, Letter issued by National Population Register (containing details of name, address)' ". This message has to come from backend.
from Table basis of error code
http://10.0.76.105:8080/browse/SD-1788
| 2020-12-24 | Branch details and Nominee details | All Nominee Validations to be added as per attachment - Word document | BE/FE | Jasemine/Parth | 29th Dec 2020 | 29th Dec 2020
| 2020-12-24 | Profile details | Customer Profiler Page Validation - Word Document | BE/FE | Ganesh/ Deepen/Rajesh S | 2020-12-29 | 29th Dec 2020
| 2020-12-24 | Profile details/Preview page | Referral Code field missing to be the Referral Lead Generator and RM Code | BE/FE | Ganesh | 2020-12-29 | 29th Dec 2020
| 2020-12-24 | Branch details and nominee details | · Field name to be titled as Nominee’s relationship with Account Holder | Front End | Parth | 2020-12-29 | 2020-12-29
45 | 2020-12-24 | Branch details and nominee details | · Nominee name should not be same as applicant (Full Name matching to be considered). | Front End | Parth | 2020-12-29 | 2020-12-29
| 2020-12-24 | Branch details and nominee details | · Nominee name should not be same as guardian name (Full Name matching to be considered). | Front End | Parth | 2020-12-29 | 2020-12-29
| 2020-12-24 | Branch details and nominee details | · DOB of nominee should not be same as applicant except relationships - Brother/Sister, Husband/Wife | Front End | Parth | 2020-12-29 | 2020-12-29
| 2020-12-24 | Branch details and nominee details/Profile details | · If marital status is Unmarried, then "Husband" and "Wife" should not be allowed in nominee relationship. | Front End | Parth | 2020-12-29 | 2020-12-29
|  | Branch details and nominee details/Profile details | · If marital status is Unmarried, then "Husband" and "Wife" should not be allowed in nominee relationship. | Back End | Jasemine | 2020-12-29 | 2020-12-29
| 2020-12-24 | Branch details and nominee details | · If Nominee is appointed and relationship is husband/wife / Father / mother, Grandmother, Grand Father, Mother in Law, Father In Law validation on nominee age should be more than 18. | Front End | Parth | 2020-12-29 | 2020-12-29
| 2020-12-24 | Branch details and nominee details | · Father, Mother, Grandmother, Grand Father, Mother in Law, Father In Law DOB should not be less than applicant's DOB on nominee page. | Front End | Parth | 2020-12-29 | 2020-12-29
| 2020-12-24 | Branch details and nominee details | · For Gender Male, Nominee should not be HUSBAND | Front End | Parth | 2020-12-29 | 2020-12-29
| 2020-12-24 | Branch details and nominee details | · For Gender Female, Nominee should not be WIFE | Front End | Parth | 2020-12-29 | 2020-12-29
| 2020-12-24 | Branch details and nominee details | · If Nominee is husbandthen marital status can not be married/widowed. | Front End | Parth | 2020-12-29 | 2020-12-29
| 2020-12-24 | Branch details and nominee details | · In Case Nominee Relation is Wife/Husband, then Spouse Name should be defaulted in Nominee Name | Front End | Parth | 2020-12-29 | 2020-12-29
| 2020-12-24 | Branch details and nominee details | · In Case Nominee Relation is Father, then Father Name should be defaulted as Nominee Name | Front End | Parth | 2020-12-29 | 2020-12-29
| 2020-12-24 | Branch details and nominee details | The session data(relationship of nominee with account holder) is required on profile page | Backend | Jasemine | 2020-12-29 | 2020-12-29
| 2020-12-24 | Profile details | Housewife(Please add this in occupation type)-Housewife(FCR codeis required by Astha for housewife)(Please add this in occupation type) | Backend | Vishal Nagula | 2020-12-29 | 2020-12-29
| 2020-12-24 | Profile details | Self employed- Please add this in occupation type)-FCR codeis required by Astha for housewife)(Please add this in occupation type) | Backend | Vishal Nagula | 2020-12-29 | 2020-12-29
| 2020-12-24 | Profile details | Diplomat - Please add this in occupation type)-FCR codeis required by Astha for housewife)(Please add this in occupation type) | Backend | Vishal Nagula | 2020-12-29 | 2020-12-29
| 2020-12-24 | Profile details | LOV matching annual income- There is difference between provided data and present data - Need to correct | Backend | Jasemine | 2020-12-29 | 2020-12-29
| 2020-12-24 | Profile details |  | Backend | Ganesh/ Rajesh S | 2020-12-29 | 2020-12-29
The pension should be auto populated on the basis of retired- occ type
dynamically maintenance
| 2020-12-24 | Profile details | To be put as hard stop. Account should not proceed ahead. If the customer changes the occupation to any other, should allow to proceed – we should not be able to create /proceed with account creation – Will lock them and will tell visit the branch | Front End | deepen | 2020-12-29 | 2020-12-29
Hard Stop. Error Message “Please visit your nearest branch for ac opening
| 2020-12-24 | Profile details | To be put as hard stop. Account should not proceed ahead. If the customer changes the occupation to any other, should allow to proceed – we should not be able to create /proceed with account creation – Will lock them and will tell visit the branch | Back end | Ganesh | 2020-12-29 | 2020-12-29
Hard Stop. Error Message “Please visit your nearest branch for ac opening
| 2020-12-24 | Profile details | Referral Lead Generator and RM Code - Label name to be incorporated on profile page - Non mandatory field -below transaction pattern section - Apply referral code section needs to be there under which Referral Lead Generator and RM Code label should be incorporated | Front End | Priyanka | 28th Dec 2020 | 29th Dec 2020
Employment code will be our referral code- 7 numeric- should be greater than 0 validation required.
| 2020-12-24 | Profile details | Referral Lead Generator and RM Code - Label name to be incorporated on profile page - Non mandatory field -below transaction pattern section - Apply referral code section needs to be there under which Referral Lead Generator and RM Code label should be incorporated | Back End | Vishal | 29th Dec 2020 | 29th Dec 2020
Employment code will be our referral code- 7 numeric- should be greater than 0 validation required.
| 2020-12-24 | Funding details page | 50 char validation in UPI field - VPA, payer name, remark in UPI screen- Please refer Vinod's sir mail for screenshots | Front End | Priyanka | 28th Dec 2020 | 29th Dec 2020
| 2020-12-24 | Final Screen | join video kyc button on success page - click - this functionality under integration - Please refer Vinod's sir mail for screenshots | Front end | Priyanka | 28th Dec 2020 | 29th Dec 2020
| 2020-12-24 | Final Screen | Addition of three fields on successful page - Please refer Vinod's sir mail for screenshots - debit card , Initial funding, Mobile banking token | Front end | Priyanka | 28th Dec 2020 | 29th Dec 2020
| 2020-12-24 | Final Screen | show debit card number masked on final screen - Please refer Vinod's sir mail for screenshots | Front end | Priyanka | 28th Dec 2020 | 29th Dec 2020
| 2020-12-24 | Personal details and address details | 1. No ammendments (removal of hyphen) has to be done in Adhaar card address. | Front End /BackEnd | Parth /ganesh | 29th Dec 2020 | 29th Dec 2020
2. Landmark edit can be given for separate field Landmark 2
3. Microservices is there for handling the address scenario with Deepak Mishra, BSG will check and get back to us.
4. In case there is no confirmation received on microservices then we have to ensure address fits in Address line 1,2,3,Landmark of personal details and address details page for addressreceived from adhaar as in house no., street, location and landmark
Logic provided :
House No+street+Location+Landmark = Merge It
Divide it into 40-40 chars to fit in add lines in yes rapido personal details and address details page, 40 characters provided if landmark is of more than 40 characters, it might come in address line 3
| 2020-11-24 | Personal details and address details | 1. Father name field will be editable in all the scenarios. | Front End /BackEnd | Parth /ganesh | 29th Dec 2020 | 29th Dec 2020
2. The fathername will be auto populated where ContactPerson is starting from S/O or D/O and the field will be still editable.